## Initial Plan
Color Coding |  |  | Completed |  |  |  | FALL 2020 SEMESTER
In Progress
[6 empty] | Week # | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
[6 empty] | Date | 2020-08-25 | 2020-09-01 | 2020-09-08 | 2020-09-15 | 2020-09-22 | 2020-09-29 | 2020-10-06 | 2020-10-13 | 2020-10-20 | 2020-10-27 | 2020-11-03 | 10--Nov | 2020-11-17 | 2020-11-24
Project Phase | Activity |  | Task Owner Name | Start Date | End Date | Progress %
Project Initiation | Discuss project proposals |  | ALL | 2020-08-25 | 2020-09-01 | 100%
| Confirm Project Team Roles |  | ALL | 2020-08-25 | 2020-08-25 | 100%
| Develop two business cases |  | Pratesh Gartaula | 2020-08-25 | 2020-09-01 | 100%
| Develop Project Initiation Document (PID) |  | Rohan Singh | 2020-09-01 | 2020-09-08 | 100%
| Produce initial Project Plan, RACI |  | Pratesh Gartaula | 2020-09-08 | 2020-09-15 | 100%
MILESTONE 1: INITIAL PROJECT PLAN COMPLETED
Requirements Definition | Produce BRM diagram, define User Roles |  | Product Owner | 2020-09-15 | 2020-09-22 | 100%
| Produce Context Diagram, Define System Interfaces |  | ALL | 2020-09-15 | 2020-09-22 | 100%
| Define Business Requirements |  | Annet John/Pratesh | 2020-09-15 | 2020-09-22 | 100%
| Agree to System Requirements types |  | All | 2020-09-15 | 2020-09-29 | 100%
| Define Functional Decomposition |  | All | 2020-09-22 | 2020-09-29 | 100%
| produce RCT documents |  | Annet John | 2020-09-22 | 2020-09-29 | 100%
| Decide which features to implement this semester |  | All | 2020-09-22 | 2020-10-06 | 100%
| Produce analysis diagrams (UML, DFD) |  | Annet John/Pratesh | 2020-09-22 | 2020-10-06 | 100%
| Define functional requirements (User Stories) |  | Annet john/Pratesh | 2020-09-22 | 2020-10-06 | 100%
| Update Project Plan with additional requirements tasks |  | Pratesh Gartaula | 2020-09-22 | 2020-10-06 | 100%
MILESTONE 2: REQUIREMENTS COMPLETED
Design | Architecture design (2 diagrams) |  | Annet John | 2020-10-06 | 2020-10-27 | 100%
| Database Design (ERD, Table spec) |  | Dac Vu | 2020-10-06 | 2020-10-20 | 100%
| System Interface Design |  | Samarth | 2020-10-06 | 2020-10-27 | 100%
| User interface design |  | Samarth | 2020-10-06 | 2020-10-27 | 100%
MILESTONE 3: DESIGN COMPLETED
Code | 01.01 Create an Account | Core Functionality | Samarth/Dac Vu | 2020-10-27 | 2020-11-03 | 100%
|  | GUI Features | Samarth/Dac Vu | 2020-10-27 | 2020-11-03 | 100%
|  | FV - Field Validation | Samarth/Dac Vu | 2020-10-27 | 2020-11-03 | 100%
|  | DF-out - Data Flow out | Samarth/Dac Vu | 2020-10-27 | 2020-11-03 | 100%
| 01.02 Sign-in into account | Core Functionality | Samarth/Dac Vu | 2020-10-27 | 2020-11-03 | 100%
|  | GUI Features | Samarth/Dac Vu | 2020-10-27 | 2020-11-03 | 100%
|  | FV - Field Validation | Samarth/Dac Vu | 2020-10-27 | 2020-11-03 | 100%
|  | DDD - Data-Driven Defaults | Samarth/Dac Vu | 2020-10-27 | 2020-11-03 | 100%
|  | DF-In - Data Flow In | Samarth/Dac Vu | 2020-10-27 | 2020-11-03 | 100%
|  | SI-In System Interface (inbound) | Samarth/Dac Vu | 2020-10-27 | 2020-11-03 | 100%
MILESTONE 4: CODING COMPLETED
Integration & Testing | Plan testing, produce a Test Plan document |  | Samarth/ Dac Vu | 2020-11-03 | 2020-11-10 | 100%
| Evaluate Features to be Tested |  | Samarth/ Dac Vu | 2020-11-03 | 2020-11-10 | 100%
| Design Test Cases |  | Samarth/ Dac Vu | 2020-11-03 | 2020-11-10 | 100%
| Execute Test Cases |  | Samarth/ Dac Vu | 2020-11-03 | 2018-04-10 | 100%
| Anaylze Test Results |  | ALL | 2020-11-03 | 2020-11-10 | 100%
MILESTONE 5: TESTING COMPLETED
Project Presentation | Prepare Application Demo for the Presentation |  | ALL | 2020-11-10 | 2020-11-24 | 100%