## I1
Task # | Module Name | RCT.ID | Core Feature | Task Description | Start Date | End Date | Status | Task Owner
0 | 0.1 Home Page | 1.01 | 01.01 Create an Account | Created the GUI features for creating an account | 2020-10-27 | 2020-11-03 | 100% | Samarth Gowda
0 | 0.1 Home Page | 1.01 | 01.01 Create an Account | Implement the local server to save the data | 2020-11-03 | 2020-11-10 | 100% | Samarth Gowda
0 | 0.1 Home page | 1.01 | 01.01 Create an Account | Implement bycrypt function to hash the password | 2020-11-03 | 2020-11-10 | 100% | Samarth Gowda
0 | 0.1 Home page | 1.02 | 01.02 Sign-in into account | Created the GUI features for Sign-in into the account | 2020-10-27 | 2020-11-03 | 100% | Samarth Gowda
0 | 0.1 Home page | 1.02 | 01.02 Sign-in into account | Implement the server to compare the hashed password and signin into the application | 2020-11-06 | 2020-11-10 | 100% | Samarth Gowda
0 | 0.1 Home page | 1.02 | 01.02 Sign-in into account | Create a Sign Up Button to redirect to registration page | 2020-10-27 | 2020-11-03 | 100% | Samarth Gowda
1 | 02. Workout Plan Schedule Menu | 2.01 | 02.01 Browse the type of workout | Create the Header of the dashboard | 2021-02-20 | 2021-03-05 | 100% | Samarth Gowda
2 | 02. Workout Plan Schedule Menu | 2.01 | 02.01 Browse the type of workout | Implement the Search Engine bar to fetch the Workout API | 2021-02-20 | 2021-03-05 | 100% | Samarth Gowda
3 | 02. Workout Plan Schedule Menu | 2.01 | 02.01 Browse the type of workout | Implement the Videolist component to get all the workout videos | 2021-02-20 | 2021-03-05 | 100% | Samarth Gowda
4 | 02. Workout Plan Schedule Menu | 2.01 | 02.01 Browse the type of workout | Implement the Videoitem component to display the selected video | 2021-02-20 | 2021-03-05 | 100% | Samarth Gowda
5 | 02. Workout Plan Schedule Menu | 2.01 | 02.01 Browse the type of workout | Implement the Videodetails component to display details of the selected video | 2021-02-20 | 2021-03-05 | 100% | Samarth Gowda
6 | 02. Workout Plan Schedule Menu | 2.01 | 02.01 Browse the type of workout | Create the corresponding GUI requirements | 2021-02-24 | 2021-03-05 | 100% | Samarth Gowda
7 | 02. Workout Plan Schedule Menu | 2.01 | 02.01 Browse the type of workout | Create a search bar GUI | 2021-02-24 | 2021-03-05 | 100% | Samarth Gowda
8 | 02. Workout Plan Schedule Menu | 2.01 | 02.01 Browse the type of workout | Test Browse the type of workout | 2021-02-24 | 2021-03-05 | 100% | Dac Vu
9 | 02. Workout Plan Schedule Menu | 2.02 | 02.02 Level of Intensity | Search for a proper API | 2021-02-27 | 2021-03-05 | 100% | Dac Vu
10 | 02. Workout Plan Schedule Menu | 2.02 | 02.02 Level of Intensity | Implement API | 2021-02-27 | 2021-03-05 | 100% | Dac Vu
11 | 02. Workout Plan Schedule Menu | 2.02 | 02.02 Level of Intensity | Create two level buttons | 2021-02-24 | 2021-03-05 | 100% | Dac Vu
12 | 02. Workout Plan Schedule Menu | 2.02 | 02.02 Level of Intensity | Implement core functionality | 2021-02-24 | 2021-03-05 | 100% | Dac Vu
13 | 02. Workout Plan Schedule Menu | 2.02 | 02.02 Level of Intensity | Implement GUI requirements | 2021-02-24 | 2021-03-05 | 100% | Dac Vu
14 | 02. Workout Plan Schedule Menu | 2.02 | 02.02 Level of Intensity | Test Level of Intensity | 2021-02-27 | 2021-03-05 | 100% | Dac Vu
15 | 02. Workout Plan Schedule Menu | 2.02 | 02.02 Level of Intensity | Re-designed the GUI of Two level buttons | 2021-02-24 | 2021-03-05 | 100% | Samarth Gowda
16 | 02. Workout Plan Schedule Menu | 2.02 | 02.02 Level of Intensity | Created a Route the display level of intensity | 2021-03-24 | 2021-03-05 | 100% | Samarth Gowda

## I2
Task # | Module Name | RCT.ID | Core Feature | Task Description | Start Date | End Date | Status | Task Owner
1 | 06. Sponsored Post and Listings | 6.01 | 06.01 Ads and Promo's | Search and create account for Google Adsense API | 2021-03-14 | 2021-03-14 | 100% | Dac Vu
2 | 06. Sponsored Post and Listings | 6.01 | 06.01 Ads and Promo's | Code the Google Adsense API component | 2021-03-14 | 2021-03-14 | 100% | Dac Vu
3 | 06. Sponsored Post and Listings | 6.01 | 06.01 Ads and Promo's | Code the local advertisement component | 2021-03-14 | 2021-03-14 | 100% | Samarth Gowda
4 | 06. Sponsored Post and Listings | 6.01 | 06.01 Ads and Promo's | Create the corresponding GUI requirements | 2021-03-14 | 2021-03-14 | 100% | Samarth Gowda
5 | 06. Sponsored Post and Listings | 6.01 | 06.01 Ads and Promo's | Test Ads and Promo's | 2021-03-14 | 2021-03-14 | 100% | Annet
6 | 03. Nutrition Program | 3.01 | 03.01 Recipes | Implement core functionality | 2021-03-10 | 2021-03-12 | 100% | Samarth Gowda
7 | 03. Nutrition Program | 3.01 | 03.01 Recipes | Implement GUI requirements | 2021-03-13 | 2021-03-13 | 100% | Rohan Singh
8 | 03. Nutrition Program | 3.01 | 03.01 Recipes | Fetch recipes from Firebase | 2021-03-14 | 2021-03-16 | 100% | Dac Vu
9 | 03.Nutrition Program | 3.01 | 03.01 Recipes | Create Calorie Counter Component | 2021-03-15 | 2021-03-20 | 100% | Samarth Gowda
10 | 03.Nutrition Program | 3.01 | 03.01 Recipes | Implemente calculation cross cutting concern to calculate the total calories intake | 2021-03-16 | 2021-03-21 | 100% | Samarth Gowda
11 | 03.Nutrition Program | 3.01 | 03.01 Recipes | Create corresponding GUI requirements | 2021-03-17 | 2021-03-22 | 100% | Samarth Gowda
12 | 03.Nutrition Program | 3.01 | 03.01 Recipes | Test Recipes | 2021-03-21 | 2021-03-22 | 100% | Pratesh

## I3
Task # | Module Name | RCT.ID | Core Feature | Task Description | Start Date | End Date | Status | Task Owner
1 | 04. Dashboard | 4.01 | Workout Statistics | Create the GUI features for statistic | 2021-03-27 | 2021-04-09 | 100% | Dac Vu
2 | 04. Dashboard | 4.01 | Workout Statistics | Implement database using Firebase to store and fetch the data | 2021-03-27 | 2021-04-09 | 100% | Dac Vu
3 | 04. Dashboard | 4.01 | Workout Statistics | Implement calculation BMI | 2021-03-28 | 2021-04-09 | 100% | Dac Vu
4 | 04. Dashboard | 4.01 | Workout Statistics | Redesign UI of Dashboard | 2021-03-28 | 2021-04-09 | 100% | Samarth
5 | 04. Dashboard | 4.01 | Workout Statistics | Testing dashboard - Core Functionalities | 2021-04-04 | 2021-05-04 | 100% | Rohan
6 | 04. Dashboard | 4.01 | Workout Statistics | Testing dashboard -GUI Features | 2021-04-04 | 2021-05-04 | 100% | Rohan
7 | 04. Dashboard | 4.01 | Workout Statistics | Testing dashboard-FV - Field Validation - Date | 2021-04-04 | 2021-05-04 | 100% | Pratesh
7 | 04. Dashboard | 4.01 | Workout Statistics | Testing dashboard-FV - Field Validation - Gender | 2021-04-04 | 2021-05-04 | 100% | Pratesh
7 | 04. Dashboard | 4.01 | Workout Statistics | Testing dashboard-FV - Field Validation - Note | 2021-04-04 | 2021-05-04 | 100% | Pratesh
8 | 04. Dashboard | 4.01 | Workout Statistics | Testing dashboard-DDV - Data-Dependency Validation | 2021-04-04 | 2021-05-04 | 100% | Dac Vu
9 | 04. Dashboard | 4.01 | Workout Statistics | Testing dashboard - CL - Calculations | 2021-04-04 | 2021-05-04 | 100% | Annet
10 | 04. Dashboard | 4.01 | Workout Statistics | Testing dashboard-ExH - Exception Handling | 2021-03-28 | 2021-05-04 | 100% | Annett
11 | 05. Purchase Bundle | 6.01 | Freemium | Create the GUI features for user profile | 2021-03-27 | 2021-04-09 | 100% | Dac Vu
12 | 05. Purchase Bundle | 6.01 | Freemium | Implement user's plan features | 2021-03-27 | 2021-04-09 | 100% | Dac Vu
13 | 05. Purchase Bundle | 6.01 | Freemium | Testing Freemium - Core Functionalities | 2021-04-04 | 2021-05-04 | 100% | Samarth
14 | 05. Purchase Bundle | 6.01 | Freemium | Testing Freemium - GUI Features | 2021-04-04 | 2021-05-04 | 100% | Samarth

## I4
Task # | Module Name | RCT.ID | Core Feature | Task Description | Start Date | End Date | Status | Task Owner
1 | 07. User Account | 7.01 | Modify General User's Information | Implement Gui feature for user profile as sign up | 2021-04-10 | 2021-04-11 | 100%% | Samarth
2 | 07. User Account | 7.01 | Modify General User's Information | Created backend routes for modify account | 2021-04-10 | 2021-04-13 | 100%% | Samarth
3 | 07. User Account | 7.01 | Modify General User's Information | Testing User Account - Core Functionality | 2021-04-10 | 2021-04-30 | 100%% | Rohan
4 | 07. User Account | 7.01 | Modify General User's Information | Testing User Account - GUI Features | 2021-04-10 | 2021-04-30 | 100%% | Rohan
5 | 07. User Account | 7.01 | Modify General User's Information | Testing User Account - FV - Field Validation | 2021-04-10 | 2021-04-30 | 100%% | Pratesh
6 | 07. User Account | 7.01 | Modify General User's Information | Testing User Account - DF-In - Data Flow In | 2021-04-10 | 2021-04-30 | 100%% | Dac
7 | 07. User Account | 7.01 | Modify General User's Information | Testing User Account - ExH - Exception Handling | 2021-04-10 | 2021-04-30 | 100%% | Annet
8 | 07. User Account | 7.02 | Reset the Password | Testing User Account - Core Functionality | 2021-04-11 | 2021-04-30 | 100%% | Rohan
9 | 07. User Account | 7.02 | Reset the Password | Implement gui feature for resetting the password | 2121-04-11 | 2021-04-30 | 100%% | Samarth
10 | 07. User Account | 7.02 | Reset the Password | Testing User Account - GUI Features | 2021-04-11 | 2021-04-30 | 100%% | Rohan
11 | 07. User Account | 7.02 | Reset the Password | Testing User Account - FV - Field Validation | 2021-04-11 | 2021-04-30 | 100%% | Pratesh
12 | 07. User Account | 7.02 | Reset the Password | Testing User Account - ExH - Exception Handling | 2021-04-11 | 2021-04-30 | 100%% | Annet
13 | 07. User Account | 7.03 | Delete an Account | Implement Gui feature for deleting account | 2021-04-12 | 2021-05-01 | 100%% | Samarth
14 | 07. User Account | 7.03 | Delete an Account | Testing User Account - Core Functionality | 2021-04-13 | 2021-04-30 | 100%% | Rohan
15 | 07. User Account | 7.03 | Delete an Account | Testing User Account - GUI Features | 2021-04-13 | 2021-04-30 | 100%% | Rohan
16 | 07.User account | 7.03 | Delete an Account | Create backend routes for delete account | 2021-04-10 | 2021-04-20 | 100%% | Samarth