## Road Map
UniFit
|  |  | Release 1 |  | Release 2
Application Modules | Feature Backlog | Story Points | Iteration 1 - 3/12/21 | Iteration 2 - 3/26/21 | Iteration 3 - 4/16/21 | Iteration 4 - 5/7/21
Module 1 - Home Page | 01.01 Create an Account
| 01.02 Sign-in into account | [5 empty] | features implemented last semester
Module 2 - Workout Plan Schedule Menu | 02.01 Browse the type of workout | 3 | x |  |  |  | features implemented this R1 release
| 02.02 Level of Intensity | 3 | x
Module 3 - Nutrition Program | 03.01 Recipes | 3 |  | x
Module 4 - Dashboard | 04.01 Workout statistics | 4 |  |  | x
Module 5 - Purchase Bundle | 05.01 Freemium | 3 |  |  | x
Module 6 - Sponsored Post and Listings | 06.01 Ads and Promo's | 2 |  | x
Module 7 - User Account | 07.01 Modify General User's Information | 2 |  |  |  | x
| 07.02 Reset the password | 2 |  |  |  | x
| 07.03 Delete an Account | 2 |  |  |  | x
|  | Velocity : | 6 | 5 | 7 | 6

## Story Map
Epics |  | Flight Reservation System (Travelo) - User Story Map
Epic 1 - Home Page |  | Epic 1 - Home Page | Epic 2 -Workout Plan Schedule | Epic 3 - Nutrition Program | Epic 4 - Dashboard | Epic 5 - Purchase Bundle | Epic 6 -Sponsored Post and Listings | Epic 7 - User Account
Epic 2 - Work Plan Schedule | User Stories | 01.01 Create an Account | 02.01 Browse the type of workout
Epic 3 - Nutrition Program |  | 01.02 Sign-in into account | 02.02 Level of Intensity
Epic 4 - Dashboard | [8 empty] | Iteration 1
Epic 5 - Purchase Bundle |  |  |  | 03.01 Recipes |  |  | 06.01 Ads and Promo's
Epic 6 -Sponsored Post and List | [8 empty] | Iteration 2
Epic 7 - User Account |  |  |  |  | 04.01 Workout statistics | 05.01 Freemium
Iteration 3
07.01 Modify General User's Information
07.02 Reset the password
[8 empty] | 07.03 Delete an Account | Iteration 4
features implemented last semester
features implemented in Release 1