## I1
Task # | Module Name | RCT.ID | Core Feature | Task Description | Start Date | End Date | Status | Task Owner
0 | 0.1 Home Page | 1.01 | 01.01 Create an Account | Created the GUI features for creating an account | 2020-10-27 | 2020-11-03 | 100% | Samarth Gowda
0 | 0.1 Home Page | 1.01 | 01.01 Create an Account | Implement the local server to save the data | 2020-11-03 | 2020-11-10 | 100% | Samarth Gowda
0 | 0.1 Home page | 1.01 | 01.01 Create an Account | Implement bycrypt function to hash the password | 2020-11-03 | 2020-11-10 | 100% | Samarth Gowda
0 | 0.1 Home page | 1.02 | 01.02 Sign-in into account | Created the GUI features for Sign-in into the account | 2020-10-27 | 2020-11-03 | 100% | Samarth Gowda
0 | 0.1 Home page | 1.02 | 01.02 Sign-in into account | Implement the server to compare the hashed password and signin into the application | 2020-11-06 | 2020-11-10 | 100% | Samarth Gowda
0 | 0.1 Home page | 1.02 | 01.02 Sign-in into account | Create a Sign Up Button to redirect to registration page | 2020-10-27 | 2020-11-03 | 100% | Samarth Gowda
1 | 02. Workout Plan Schedule Menu | 2.01 | 02.01 Browse the type of workout | Create the Header of the dashboard | 2021-02-01 | 2021-02-01 | 100% | Samarth Gowda
2 | 02. Workout Plan Schedule Menu | 2.01 | 02.01 Browse the type of workout | Implement the Search Engine bar to fetch the Workout API | 2021-02-02 | 2021-02-02 | 100% | Samarth Gowda
3 | 02. Workout Plan Schedule Menu | 2.01 | 02.01 Browse the type of workout | Implement the Videolist component to get all the workout videos | 2021-02-02 | 2021-02-04 | 100% | Samarth Gowda
4 | 02. Workout Plan Schedule Menu | 2.01 | 02.01 Browse the type of workout | Implement the Videoitem component to display the selected video | 2021-02-04 | 2021-02-05 | 100% | Samarth Gowda
5 | 02. Workout Plan Schedule Menu | 2.01 | 02.01 Browse the type of workout | Implement the Videodetails component to display details of the selected video | 2021-02-06 | 2021-02-06 | 100% | Samarth Gowda
6 | 02. Workout Plan Schedule Menu | 2.01 | 02.01 Browse the type of workout | Create the corresponding GUI requirements | 2021-02-08 | 2021-02-09 | 100% | Samarth Gowda
7 | 02. Workout Plan Schedule Menu | 2.01 | 02.01 Browse the type of workout | Create a search bar GUI | 2021-02-09 | 2021-02-09 | 100% | Samarth Gowda
8 | 02. Workout Plan Schedule Menu | 2.01 | 02.01 Browse the type of workout | Test Browse the type of workout | 2021-02-22 | 2021-02-22 | 100% | Dac Vu
9 | 02. Workout Plan Schedule Menu | 2.02 | 02.02 Level of Intensity | Search for a proper API | 2021-02-09 | 2021-02-09 | 100% | Dac Vu
10 | 02. Workout Plan Schedule Menu | 2.02 | 02.02 Level of Intensity | Implement API | 2021-02-09 | 2021-02-14 | 100% | Dac Vu
11 | 02. Workout Plan Schedule Menu | 2.02 | 02.02 Level of Intensity | Create two level buttons | 2021-02-09 | 2021-02-14 | 100% | Dac Vu
12 | 02. Workout Plan Schedule Menu | 2.02 | 02.02 Level of Intensity | Implement core functionality | 2021-02-09 | 2021-02-15 | 100% | Dac Vu
13 | 02. Workout Plan Schedule Menu | 2.02 | 02.02 Level of Intensity | Implement GUI requirements | 2021-02-16 | 2021-02-16 | 100% | Dac Vu
14 | 02. Workout Plan Schedule Menu | 2.02 | 02.02 Level of Intensity | Test Level of Intensity | 2021-02-22 | 2021-02-22 | 100% | Dac Vu
15 | 02. Workout Plan Schedule Menu | 2.02 | 02.02 Level of Intensity | Re-designed the GUI of Two level buttons | 2021-02-21 | 2021-02-21 | 100% | Samarth Gowda

## I2
Task # | Module Name | RCT.ID | Core Feature | Task Description | Start Date | End Date | Status | Task Owner